## Sheet1
Item | Improvements | Cost | Funding Source | Year | [9 empty] | Priority | Status
|  |  |  | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
1 | Renovation (Kitchen) | 20000 | Grants ($20k) | Year 2019: 0 | Now | 80% complete | Mick
2 | Shade cloth replacement (path and court 1) | 12000 | Grants ($2.5K) | Year 2019: 9500 | Now | Planning underway | Mick
4 | Master Plan | 2500 | Cash | Year 2019: 2500 | Now | Underway | Lee
3 | Sports Dev | 2200 | Cash - Rebate | Year 2019: 1600 | Now |  | Lee
5 | Fix court 12 | 1000 | Council | [10 empty] | Now | ? | Chris
6 | Electrical Room | 3000 | Council | [10 empty] | Now | ? | Chris
7 | Renovation (Coaches room) | 2000 | Cash | Year 2019: 2000 | Now |  | Tony
8 | Renovation (Minor improvements to lower complex) | 2000 | Cash | Year 2019: 2000 | Now |  | Chris
9 | Re-surfacing courts (Courts 10-11) - Hot Shots | 40000 | Cash - Rebate | Year 2019: 20000 | High | Investigating | Tony
10 | LED replacement of Lighting (Courts 8-9) | 22727.6923 | Grant / Loan / Rebate | Year 2020: 15909.3846 | High | Grant submitted | Tony
11 | Re-fencing (Courts 12-13) | 40000 |  | Year 2020: 40000 | High
12 | Replace driveway gates | 6280 | Cash | Year 2020: 6280 | High
13 | Gates / Bollards - Entry to top car park | 3000 | Cash | Year 2020: 3000 | High
14 | Re-surfacing courts (Courts 8-9) | 17000 |  | Year 2020: 17000 | High
15 | Lower complex survey, geo-tech and other report | 20000 | Cash | Year 2020: 20000 | High
16 | DA for upper complex | 10000 | Cash | Year 2020: 10000 | High
17 | LED replacement of Lighting (Courts 1-4) | 45455.3846 | Grant / Loan / Rebate | Year 2020: 31818.7692 | High | Grant submitted
18 | New Toilets/Cafe - Upper Complex | 350000 | Council | [10 empty] | High | Planning in Progress | bar: Year 2021
19 | New landscsping | 25000 | Cash | Year 2021: 8333.3333; Year 2023: 8333.3333; Year 2026: 8333.3333 | Medium
20 | Work shed / Committee Room | 30000 | Council | [10 empty] | Medium | bar: Year 2021
21 | Re-fencing (Courts 1-4) | 42000 |  | Year 2021: 42000 | Medium
22 | Convert to Hard Court (5-7) | 70000 |  | Year 2022: 70000 | Medium
23 | LED replacement of Lighting (Courts 5-7) | 34091.5385 | Grant / Loan / Rebate | Year 2022: 23864.0769 | Medium | Grant submitted
31 | Repainting internal main clubhouse and resanding floors | 2200 | Op Exp | Year 2022: 2200 | Medium
32 | Renovation (Blue Room) | 6600 | Cash | Year 2022: 6600 | Medium
33 | Replacement of draining (next to shed / committee room) | 9516 | Council | Year 2022: 9516 | Medium
23 | LED replacement of Lighting (Courts 12-13) | 22727.6923 | Grant / Loan / Rebate | Year 2023: 15909.3846 | Medium | Grant submitted
24 | LED replacement of Lighting (Courts 10-11) | 22727.6923 | Grant / Loan / Rebate | Year 2023: 15909.3846 | Medium | Grant submitted
29 | Solar Panels (Upper Complex) | 30000 |  | Year 2023: 30000 | Medium
48 | Implement Book-a-court system | 9000 | Rebate ($6,000) | Year 2023: 3000 | Medium
28 | Re-surfacing courts (Courts 12-13) | 60000 |  | Year 2024: 60000 | Medium
41 | Re-fencing (Courts 14-17) | 50000 |  | Year 2024: 50000 | Long Term
45 | Re-surfacing courts (Courts 14-17) | 140000 |  | Year 2024: 140000 | Long Term
36 | LED Lighting (Courts 14-17) | 59392 | Grant / Loan / Rebate | Year 2025: 41574.4 | Long Term
38 | LED Lighting (Courts 22-23) | 29696 | Grant / Loan / Rebate | Year 2025: 20787.2 | Long Term
42 | Re-fencing (Courts 18-21) | 50000 |  | Year 2025: 50000 | Long Term
43 | Re-fencing (Courts 22-23) | 30000 |  | Year 2025: 30000 | Long Term
47 | Re-surfacing courts (Courts 22-23) | 70000 |  | Year 2025: 70000 | Long Term
37 | LED Lighting (Courts 18-21) | 59392 | Grant / Loan / Rebate | Year 2026: 41574.4 | Long Term
46 | Re-surfacing courts (Courts 18-21) | 140000 |  | Year 2026: 140000 | Long Term
44 | Re-surfacing courts (Courts 1-4) | 42000 |  | Year 2027: 42000 | Long Term
39 | Re-fencing (Courts 10-11) | 55000 |  | Year 2027: 55000 | Long Term
40 | Re-fencing (Courts 5-9) | 60000 |  | Year 2028: 60000 | Long Term
49 | Perimeter fencing (Lower complex) | 120000 |  | Year 2028: 120000 | Long Term
52 | Re-develop bottom complex | 1200000 | Grant | [10 empty] | Long Term | bar: Year 2028
50 | LED replacement of Lighting (Courts 1-13) | 147730
51 | LED Lighting (Courts 14-23) | 148480
| TOTALS | 1346546 |  | 37600 | 144008.1538 | 50335.3333 | 112180.0769 | 73152.1026 | 250000 | 212361.6 | 189907.7333 | 97000 | 180001